## Tasks estimation
Category | Task | Real estimation in hours | Total in hours
Infrastructure | Login - Frontend | 8 | 53-70
| Sign up - Frontend | 6
| Change password - Frontend | 3
| Authentification designer - Backend | 4
| Authentification client/user - Backend | 4
| Authentification admin - Backend | 4
| Pages arrangement - Frontend | 24
Refresh design - main | Add to database | 16 | 171 - 200
| Extract from database | 12
| Edit database | 20
| Delete from database | 12
| Password encryption | 3
| Login via Facebook & Google | 16
| E-mail notification | 16
| Add comments (design page) | 20
| First classification( designs per area ) - Frontend & Backend | 24
| Second classification ( designs per designer ) - Frontend & Backend | 24
| Contact administrator (notification via e-mail) | 8
Total in hours |  |  | 270

## Costs
Total ( Euro)
Development + Testing + Bug fixing | 5400
Maintanance / ... year | 3000 (150h) X …
Name (Refresh design) | 1200
Logo | 800
Website Advertisement | 500
Artwork | 400
Other services (APIs…) | 200
JIRA / year | 120
Design Software License / year | 150
IntelliJ / year | 1200
Hosting / year, Deployment, Set-up, Config | 1000 + 1200